## CI_CD -Tools
S.No. | Description | Tools/Services | Proposed | Suggested
1 | Code version | Gitlab | Agreed | Gitlab
2 | Code build ( if applicable) | Gitlab | Agreed | Gitlab
3 | Code quality | Sonar Qube+Git lab | Feasability | Sonar Qube
4 | Code review | Gitlab | Feasability | Chef ,Puppet
5 | Code deployment | Gitlab | Agreed | code pipeline
6 | Single commit deployment | Gitlab | Agreed
7 | Resource Provisioning | aws Terraform Template Creation-S3,EC2,Redshift cluster,Lambda,Cloud watch | Agreed
8 | Resource Provisioning | Python Template -Update Lambda | Agreed
9 | Resource provisioning | AWS Glue Job provisioning | Agreed

## Phases
Pipeline preparation
S.No. | Phases | Description | Status
1 | Tools Identified | Tools | Status
| Code version | Gitlab
| Code build ( if applicable) | Gitlab
| Code quality | Sonar Qube | POC is required
| Code review | Gitlab
| Code deployment | Gitlab
| Single commit deployment | Gitlab
2 | Tools Integration
| Git Lab |  | Integration in progress
Sonar Qube
3 | Deployment in Test /Dev env
| Resource Provisioning | Terraform Template Creation -Vlaidate ,Plan,Apply,Destroy | Implemented
|  | Terraform Resource provisioning -S3 | Implemented
Terraform Resource provisioning -EC2 instance
Terraform Resource provisioning -Lambda function defnition
Terraform Redshift Cluster
AWS Glue Job provisioning -definition
|  | Python Template -Lint,Test ,Build,Deploy | Implemented In local
Python Resource provisioning -AWS Lambda function Body
AWS Glue Job provisioning -Body
4 | Deployment in Prod env
| Resource Provisioning | Terraform Template Creation
Terraform Resource provisioning -S3
Terraform Resource provisioning -EC2 instance
Terraform Resource provisioning -Lambda function defnition
Terraform Redshift Cluster
AWS Glue Job provisioning -definition
Python Template -Lint,Test ,Build,Deploy
Python Resource provisioning -AWS Lambda function Body
AWS Glue Job provisioning -Body
| Implementation of terraform destroy stage in the pipeline | Manual
| Implementation of Python deploy stage in the pipeline | Manual
5 | Automation
| Implementation of Python deploy stage in the pipeline | Manual to automation
| Automate Code Deployment with out Test Artifacts | Lambda function deployment
| Automate Code Deployment with Test Artifacts | Lambda function deployment

## Building CI CD Pipeline
Sno | Story | Task Name | Prerequsites of AWS Service Required | Status
1 | Terraform template -Resource provisioning-S3 |  | IAM Role, S3 -Full Access | Completed
2 | Terraform template -Resource provisioning-EC2 |  | IAM Role, EC2 -Full Access | Not Completed
3 | Terraform template -Resource provisioning |  | IAM Role, VPC -Full Access | Not Completed
- VPC
4 | Terraform template -Resource provisioning |  | IAM Role, Lambda -Full Access | Not Completed
- Lambda
5 | Terraform template -Resource provisioning |  | IAM Role - Full Access | Not Completed
- Redshift Cluster
6 | Terraform - Storing State File in remote backend ( in AWS S3 Bucket ) |  | S3 and RDS | Not Completed
7 | Terraform template -Resource provisioning- |  | IAM Role | Not Completed
| AWS Glue Job provisioning |  | 1. AWS Glue Service permission
2. AWS Glue Resource Permissions
ex:- ( S3, Amazon rds. database )
3. AWS CloudWatch logs Permissions
4. AWS Key Management Services (KMS)
8 | CI/CD - Refactoring DAT Repository |  | NA | Not Completed
9 | CI/CD -DAT Repository integration with terraform |  | NA | Not Completed
10 |  |  | IAM Role
| CI/CD - Automate Code Deployment without |  | 1. Lambda function to create and update
| Test artifacts - |  | 2. Permission to create and update S3 bucket and objects
3. Permission to create and update EC2
11 |  |  | IAM Role
| CI/CD - Automation code deployment |  | 1. Lambda function to create and update
| with Test artifacts - |  | 2. Permission to create and update S3 bucket and objects
3. Permission to create and update EC2
4. Lambda -Full Access
12 | Implementation of terraform destroy stage in the pipeline
13 |  | 1. CI /CD - Lambda function deployment | IAM Role | Not Completed
| CI/CD - Automate Code Deployment without |  | 1. Lambda function to create and update
| Test artifacts |  | 2. Permission to create and update S3 bucket and objects
3. Permission to create and update EC2
2. CI / CD - SQL Code deployment into redshift
3. Glue Jobs
4. Nifi
14 | CI /CD UI - Interface ( ex -Dropdown )
15 |  | 1. SQL deployment - system testing ( connection) | IAM Role | Not Completed
| CI/CD - Automation code deployment |  | 1. Lambda function to create and update
| with Test artifacts |  | 2. Permission to create and update S3 bucket and objects
3. Permission to create and update EC2
4. lambda -Full Access
2. identify the testcases
3. common testcases
4. functional testcases